## Cover
SIMRAN'S SPACE · TEMPLATES
Impact Analysis Template
A reusable framework for analyzing product launches, experiments, and feature releases — from hypothesis to executive summary, with AI-ready export prompts.
WHAT'S INSIDE
◆ | Project Details — hypothesis, owner, and success metrics in one place
◆ | Release Timeline — phase-by-phase status with color-coded tracking
◆ | KPI Tracking + Before vs. After Comparison, both formula-driven
◆ | Weekly Trends chart, Insights, Risks, and Recommendations logs
◆ | Executive Summary that pulls its numbers live from your data
◆ | An AI Prompts tab — copy-ready prompts for ChatGPT or Claude
WHO IT'S FOR
Built for both technical and non-technical users — product managers writing the executive summary, and analysts filling in the KPI tracking, working from the same file.
Built by Simran Tiwari — simrant.github.io

## Read Me
How to use this template
1. Start with Project Details
Fill in the hypothesis and success metrics before you launch — deciding what "success" looks like after the fact is how good analyses turn into bad ones.
2. Track the Release Timeline
One row per phase. The Status dropdown color-codes itself, so a glance at the tab tells you where things stand.
3. Log KPI Tracking weekly
Same metrics every week, same units. The Before vs. After Comparison and Weekly Trends chart both pull from this tab automatically.
4. Fill Insights, Risks, and Recommendations as you go
Don't wait until the end — the best insights get lost if you wait for the retro to write them down.
5. Executive Summary writes most of itself
Every number on it is a formula pulling from KPI Tracking and Before vs. After. You only need to fill in the two verdict cells at the bottom.
6. Use the AI Prompts tab when you export
Copy your KPI Tracking or Before vs. After table into ChatGPT or Claude alongside the matching prompt — they're written to ask for exactly the kind of analysis this template is built around.
Why this one's different
Most impact-analysis templates are either a blank table or a rigid dashboard that only works for one kind of launch. This one separates the raw log (KPI Tracking, Risks, Insights) from the synthesis (Executive Summary) so it works the same way whether you're analyzing an A/B test, a feature release, or a full product launch — and the AI Prompts tab means the handoff to a stakeholder-ready writeup takes minutes, not another meeting.

## Project Details
Project Details
Project name | New checkout flow experiment
Owner
Launch date | 2026-06-01
Analysis date | 2026-07-10
Hypothesis | Reducing checkout from 4 steps to 2 will increase conversion rate without increasing cart abandonment.
Success metrics | Conversion Rate, Cart Abandonment Rate, Revenue per Visitor
Stakeholders | Product, Engineering, Growth
Status | In Progress

## Release Timeline
Release Timeline
Phase | Owner | Start Date | End Date | Duration (days) | Status
Discovery & hypothesis | Priya | 2026-05-01 | 2026-05-10 | 9 | Complete
Design & prototyping | Diego | 2026-05-11 | 2026-05-20 | 9 | Complete
Build | Engineering | 2026-05-21 | 2026-05-31 | 10 | Complete
Launch (10% rollout) | Growth | 2026-06-01 | 2026-06-07 | 6 | Complete
Full rollout | Growth | 2026-06-08 | 2026-06-21 | 13 | In Progress
Post-launch analysis | Analyst | 2026-06-22 | 2026-07-10 | 18 | Not Started

## KPI Tracking
KPI Tracking
Metric | Target | Week 1 | Week 2 | Week 3 | Week 4 | % vs Target
Conversion Rate (%) | 4.5 | 3.8 | 4.1 | 4.4 | 4.7 | 4.444%
Cart Abandonment (%) | 62 | 68 | 65 | 63 | 61 | -1.613%
Revenue per Visitor ($) | 3.2 | 2.85 | 3.05 | 3.15 | 3.35 | 4.688%
Daily Active Users | 12000 | 11400 | 11800 | 12100 | 12600 | 5%
Support Tickets (checkout) | 40 | 58 | 51 | 44 | 38 | -5%

## Before vs After
Before vs. After Comparison
Metric | Before | After | % Change | Notes
Conversion Rate (%) | 3.8 | 4.7 | 23.68% | Hypothesis confirmed — fewer steps converted more visitors.
Cart Abandonment (%) | 68 | 61 | -10.29% | Slightly worse than hoped; watch closely during full rollout.
Revenue per Visitor ($) | 2.85 | 3.35 | 17.54% | Strong lift, driven by the conversion rate gain.
Daily Active Users | 11400 | 12600 | 10.53% | Grew in line with normal traffic trends, not launch-driven.
Support Tickets (checkout) | 58 | 38 | -34.48% | Spike during rollout week, tapering off as UI settled.

## Weekly Trends
Weekly Trends
Charted straight from KPI Tracking — update that tab and this redraws itself.
Normalized index (Week 1 = 100)
Metric | Week 1 | Week 2 | Week 3 | Week 4
Conversion Rate (%) | 100 | 107.8947 | 115.7895 | 123.6842
Cart Abandonment (%) | 100 | 95.5882 | 92.6471 | 89.7059
Revenue per Visitor ($) | 100 | 107.0175 | 110.5263 | 117.5439
Daily Active Users | 100 | 103.5088 | 106.1404 | 110.5263
Support Tickets (checkout) | 100 | 87.931 | 75.8621 | 65.5172

## Insights
Insights
Insight | Evidence | Impact
Shorter checkout converts better, but only after the second week | Conversion rate dipped in Week 1 (3.8%) before climbing past baseline by Week 4 (4.7%) — users needed to get used to the new flow | High
Support tickets spiked during rollout, not after | Tickets peaked at 58 in Week 1 and fell every week after — a rollout communication issue, not a lasting product problem | Medium
Cart abandonment improvement is smaller than the conversion gain | Abandonment only fell from 68% to 61%, while conversion rose 24% relative — the two metrics aren't moving in lockstep | Medium

## Risks
Risks
Risk | Likelihood | Impact | Risk Score | Mitigation
Full rollout repeats the Week 1 support spike | Medium | Medium | 4 | Pre-write a support macro and give the team a heads-up before rollout expands
Conversion gain doesn't hold once novelty wears off | Low | High | 3 | Re-measure at the 60-day mark, not just 30
Abandonment stays flat while conversion keeps rising | Medium | Low | 2 | Watch for users converting on lower-intent visits — check downstream refund rate

## Recommendations
Recommendations
Recommendation | Owner | Priority | Status
Proceed to 100% rollout | Priya | High | In Progress
Add a support macro before expanding rollout | Support Lead | High | Not Started
Re-measure conversion at 60 days, not just 30 | Analyst | Medium | Not Started
Investigate why abandonment isn't falling as fast as conversion is rising | Diego | Medium | Not Started

## Executive Summary
Executive Summary
New checkout flow experiment — analyzed Dec 30, 1899
Conversion Rate | Cart Abandonment | Revenue / Visitor | Daily Active Users
23.68% | -10.29% | 17.54% | 10.53%
Top insight
Shorter checkout converts better, but only after the second week
Top risk
Full rollout repeats the Week 1 support spike
Top recommendation
Proceed to 100% rollout
Overall verdict (fill in)
Ship it. The conversion gain outweighs the modest abandonment improvement, and the support spike was a rollout-communication issue, not a product flaw.

## AI Prompts
AI Prompts
Export the tab mentioned, paste it into ChatGPT or Claude above the prompt, and send both together.
Summarize the impact
Export: KPI Tracking + Before vs After
Paste your KPI Tracking and Before vs After tables above this prompt. Summarize the impact of this launch in 3 bullet points a busy exec would actually read, using the real numbers, not vague language like "significant improvement."
Find risks I might be missing
Export: KPI Tracking + Insights
Paste your KPI Tracking and Insights tables above this prompt. Based on these trends, what risks or failure modes should I be watching for in the next 30 days that aren't already on my Risks tab? Be specific about which metric would move first as an early warning sign.
Draft executive summary bullets
Export: Before vs After + Insights
Paste your Before vs After and Insights tables above this prompt. Write 4 executive summary bullets for a non-technical stakeholder audience, in plain language, leading with the business impact rather than the metric names.
Suggest follow-up experiments
Export: Before vs After
Paste your Before vs After table above this prompt. Given these results, suggest 2-3 specific follow-up experiments that would either strengthen confidence in this result or test the next logical improvement.
Explain a metric decline
Export: KPI Tracking (single metric)
Paste one row of weekly data for a metric that declined above this prompt. Give me 3 plausible explanations for this decline, ranked by likelihood, and what data I'd need to check to confirm or rule out each one.